## Sheet1
ASSETS DELIVERY WORKING GROUP
CRANBROOK TOWN COUNCIL
24 JUNE 2024
ADOPTION
Asset | Snagging | Delivery Date | Current Position | Comments
Land transfers of public open space | Awaiting confirmation from consortium that land has been completed to specification
Tulip Way development | Gabion wall finishing and future adoption by Devon County Council. Issues around access to potential areas of public open space across private land. Transfer of areas of public open space to social housing provider. Safety barrier along north boundary of Ecology Park. Identification of areas of public open space to be adopted by Cranbrook Town Council. |  | Taylor Wimpey to provide a sketch of the proposed alternative to the ramp on parcel 7 to the planning authority. As at 24.11.2023 the ramp issue was still outstanding. Other adoption issues ongoing. Public open space south of Rush Meadow Road (opposite Allotments) in current land transfer proposals above - pending remediation.
Persimmon Parcel - phase 4 - Cedar Close parking on planned Public Open Space |  |  | Design proposals to create permeable parking areas on the existing grass verge subject of a site meeting with Persimmon, planning authority and Town Council 4.10.23. General approach agreed - acceptable to Town Council to manage the remaining verge and hedgerow as and when transferred by Persimmon. Persimmon to submit final design to planning authority for agreement.
COUNTRY PARK & NATURE RESERVES
Asset | Snagging | Delivery Date | Current Position | Comments
Sustainable Urban Drainage Systems (Phases 2 & 3 as per plan 30) | Phase 2 (Stone Meadow) & the small basin off Westland Way/Crannaford Lane, town centre basins | Basins 2A/B/C. Planning Permission granted for extension of basin 2C. Awaiting timescales for work, expected 2024. Town centre basins await construction.
Sustainable Urban Drainage Systems (Phases 2 & 3 as per plan 30) | Phase 3 (Ecology Park, Platinum Park, Island Avenue, Ingrams, Yonder Acre Way) | Awaits completion of the Ecology Park basins and drainage system (including the syphon and Viewing Platform), plus the yet to be constructed basin north of Ingrams.
Remediation following E.ON's installation of eastern transmission main pipe extension |  |  | Eastern transmission main complete. Meeting held between E.ON, Ranger and Cllr Ray Bloxham on 4 July 2023. Programme of remediation and finishing works agreed with E.ON. Includes weed treatment, ground aeration, levelling and seeding, hedgerow gapping, path repair, scrape seeding and screening planting. Agreed seasonal programme for new planting of hedgerow and screening in autumn. | Haul road removed. Ground to the east of the new bridge remediated, aerated and re-seeded. Bridge opened with new safety fence installed. New scrape to the west of the bridge still to be seeded. Screening planting and hedge gapping to be carried out this autumn. Land to the west of the bridge has been subject to some remediation but remains very wet. Discussed at Amenities Committee 9-10-23 to determine future designation prior to remediation. Ranger and Cranbrook Town Council Chair undertook to produce a scheme for the future of the area. Screening planting and hedgerow gapping completed Nov. ’23. Discussions with E.ON to extend pathway to Western entrance.
SPORTS
Asset | Snagging | Delivery Date | Current Position | Comments
Ingrams Multi-Use Games Area (MUGA) |  |  | Tender underway; Council to consider on 24 June 2024.
Ingrams LEAP (Local Equipped Area for Play) |  |  | Trigger point 2,750 occupations. Awaiting timescale for the ground preparation (consortium obligation) to enable the process for delivery of the play area to commence.
Ingrams Pavilion |  |  | Awaiting power connection and provision of heat and hot water.
Trim trail within Stone Meadow Country Park |  |  | Consortium consented to change of location; asset delivery working group researching options.
PLAY PARKS
Asset | Snagging | Delivery Date | Current Position | Comments
Neighbourhood Equipped Area of Trail within Stone Meadow Country Park |  |  | Expansion plans for basin 2C should accommodate Neighbourhood Equipped Area of Play.
Local Equipped Area of Play for Town Centre/Cranbrook Education Campus |  |  | Trigger 3,250 homes - awaiting planning approval for attenuation tank to be installed before works to deliver play park can commence.
INFRSTRUCTURE
Asset | Snagging | Delivery Date | Current Position | Comments
Town square |  |  | Under construction.
Delivery of The Tillhouse |  |  | Awaiting town centre masterplan and allocation of land for Cranbrook Town Council.
Provision for Scout hut |  |  | Planning authority confirmed that the hut is not included in the infrastructure delivery plan attached to the Cranbrook Plan and that they are not including the provision in any Section 106 negotiations relating to the expansion areas.
Delivery of grounds maintenance compound |  |  | Discussions with planning authority ongoing.
Southbrook Allotments |  |  | Await handover of allotments which awaits the completion of adjacent construction.
CCTV |  |  | Assessing CCTV provision for Hayes Square play area, skatepark and town square. Discussions continue with the consortium who are obligated to provide electricity and water connections to play parks.