## Sheet1
ASSETS DELIVERY WORKING GROUP
CRANBROOK TOWN COUNCIL
22 JULY 2024
ADOPTION
Asset | Snagging | Delivery Date | Current Position | Comments
Land transfers of public open space | Awaiting new set of transfer plans
Tulip Way development | Gabion wall finishing and future adoption by Devon County Council. Issues around access to potential areas of public open space across private land. Transfer of areas of public open space to social housing provider. Safety barrier along north boundary of Ecology Park. Identification of areas of public open space to be adopted by Cranbrook Town Council. |  | Taylor Wimpey to provide a sketch of the proposed alternative to the ramp on parcel 7 to the planning authority. As at 24.11.2023 the ramp issue was still outstanding. Other adoption issues ongoing. Public open space south of Rush Meadow Road (opposite Allotments) in current land transfer proposals above - pending remediation.
Persimmon Parcel - phase 4 - Cedar Close parking on planned Public Open Space |  |  | Design proposals to create permeable parking areas on the existing grass verge subject of a site meeting with Persimmon, planning authority and Town Council 4.10.23. General approach agreed - acceptable to Town Council to manage the remaining verge and hedgerow as and when transferred by Persimmon. Persimmon to submit final design to planning authority for agreement.
COUNTRY PARK & NATURE RESERVE
Asset | Snagging | Delivery Date | Current Position | Comments
Sustainable Urban Drainage Systems (Phases 2 & 3 as per plan 30) | Phase 2 (Stone Meadow) & the small basin off Westland Way/Crannaford Lane, town centre basins | Basins 2A/B/C. Planning Permission granted for extension of basin 2C. Awaiting timescales for work, expected 2024. Town centre basins await construction.
Sustainable Urban Drainage Systems (Phases 2 & 3 as per plan 30) | Phase 3 (Ecology Park, Platinum Park, Island Avenue, Ingrams, Yonder Acre Way) | Awaits completion of the Ecology Park basins and drainage system (including the syphon and Viewing Platform), plus the yet to be constructed basin north of Ingrams.
SPORTS
Asset | Snagging | Delivery Date | Current Position | Comments
Ingrams Multi-Use Games Area (MUGA) |  |  | Tender submission deadline passed on 11 August 2024; tender evaluation underway
Ingrams LEAP (Local Equipped Area for Play) |  |  | Trigger point 2,750 occupations. Awaiting ground preparation (consortium obligation) to enable the process for delivery of the play area to commence.
Ingrams Pavilion |  |  | Awaiting power connection and provision of heat and hot water.
Trim trail within Stone Meadow Country Park |  |  | Tender submission deadline passed on 11 August 2024; tender evaluation underway
PLAY PARKS
Asset | Snagging | Delivery Date | Current Position | Comments
Neighbourhood Equipped Area of Trail within Stone Meadow Country Park |  |  | Expansion plans for basin 2C should accommodate Neighbourhood Equipped Area of Play.
Local Equipped Area of Play for Town Centre/Cranbrook Education Campus |  |  | Trigger 3,250 homes - awaiting planning approval for attenuation tank to be installed before works to deliver play park can commence.
INFRSTRUCTURE
Asset | Snagging | Delivery Date | Current Position | Comments
Town square |  |  | Under construction
Delivery of The Tillhouse |  |  | Awaiting town centre masterplan and allocation of land for Cranbrook Town Council
Cranbox |  |  | Exploration as per minute 24/98 dated 24 June 2024
Provision for Scout hut |  |  | Planning authority confirmed that the hut is not included in the infrastructure delivery plan attached to the Cranbrook Plan and that they are not including the provision in any Section 106 negotiations relating to the expansion areas
Delivery of grounds maintenance compound |  |  | Discussions with planning authority ongoing
Southbrook Allotments |  |  | Await handover of allotments which awaits the completion of adjacent construction
CCTV |  |  | Assessing CCTV provision for Hayes Square play area, skatepark and town square. Discussions continue with the consortium who are obligated to provide electricity and water connections to play parks