## Minutes Ref
Ingrams
Date | Minutes Ref | Description
2021-03-22 | (21/49) | Reprot setting out proposal for the Ingrams Siteand resolved to progress the development of the sports pavilion and associated infrrasructure
2021-06-28 | (21/126) | Tender document publication
2021-09-20 | (21/187) | Council considered a report summarising the tender evalua tion process and appoint ed Halsall as the preferred supplier of the design
and build of the Ingrams Pavilion and associated infrastructure. The decision by Council followed returned tenders which exceeded the stated budget for the project and Council
resol ved to work with the preferred supplier to refine their proposals to bring forward the project within budget. The Council’s a sset d elivery working g roup was requested to bring a
further report to Council on 25 October 2021outlining progress.
2021-10-25 | (21/207) | Inform Halsall that it was unable to progress their revised proposal and that the Council was reconsidering its position.
2022-01-10 | (22/8) | Appointed Healthmatic
2022-02-21 | (22/44) | Appoint Studio Four Architects
2022-04-25 | (22/73) | MUGA Tender approved for publication
2022-04-25 | (22/80) | Signed and execute the JCT DB Design and Build Contract 2016
2022-05-23 | (22/101) | Geneeral Reserve £301,750 to deliver the additional two changing rooms withint the Ingrams Pavilion
2022-07-25 | (22/136) | Established working group and refine business plan
Close the site from 1 September 2022
2022-10-24 | (22/183) | Agree to investigate the provision of temproary electricity and heating
2022-11-21 | (22/207) | Ingrams Sports Pitches Land Transfer
21/11 2022 | (22/208) | Engaged Peter Woodman Pitch Services to maintain the cricket square
2023-01-23 | (23/6 ) | Ingrams Business Plan Financial Assumptions
2023-02-20 | (23/34) | Puchase a Stothert & Pitt Roller from Poweroll at a cost of $4,645
Storage Consultation with the planning authority EDDDC
2023-03-20 | (23/50) | Puchase Cleveland Containers and installaion
2023-04-24 | (23/59) | Appoint Exe Valley Plant Hire to construct concrete base
2023-08-21 | (23/151) | Agree to the revised new budget dated 9 August 2023 covering the period from September 2023
until August 2024 to maintain the cricket square and to assume a general oversight of grounds
maintenance activities and performance at the Ingrams sports pitches.
2024-02-16 | (24/22) | Ingrams Sports Pitches Charging schedule
2024-03-18 | (24/42) | Services Connections
Contribution to EMR £50,000 from General Reserve
2024-09-23 | (24/248) | Ingrams Delivery of MUGA

## EMR337
EMR 337 - Ingrams Pavilion
Date | Supplier | Invoice Number | Description | Contract | Additional | Credit
2021-08-11 | East Devon Districat Council |  | Ingrams Money |  |  | 171135 |  | 22 March 2021 (Minutes Ref 21/49)
2021-11-11 | Persimmon Home South West |  | CTC 184 |  |  | 300000 |  | Four changing rooms, car park and associated landscaping |  |  | 600000 | Shared by Consortiums £750,000 11/11/20-12
2021-11-11 | Taylor Wimpey |  | CTC185 |  |  | 225000 |  | Country Park Resource Centre |  |  | 150000 | Invoices CTC184-186
2021-11-11 | Hallam Land Management |  | CTC186 |  |  | 225000 |  | Provision of youth play areas |  |  | 95554
2022-03-03 | Devon Air Ambulance Landing |  | Ingrams DAAT Landing Contribution |  |  | 2849.47 |  | Public art contribution |  |  | 75000
2022-05-23 | General Reserve |  | CTC (22/101) |  |  | 301750 |  | The following additional contribution has also been secured:
2022-11-11 | Sport England |  | Grants |  |  | 118750 |  | Sport England capital contribution |  |  | 125000
2022-12-21 | Sport England |  | Grants |  |  | 6250 |  |  |  | Total: | 1045554
2022-04-19 | Healthmatic | 11728 | Design & Build Contract Delivery Contract Milestone Payment 1 | 46398.98
2022-04-28 | Studio Four | 15832-42019 | Pre-Construction Stage 20% of £3,200 | 640 |  |  |  | 23/05/2022 (22/101)
2022-04-28 | Studio Four | 15832-42019 | Addition Documents : 2 x JCT Design Contract 2016 | 152 |  |  |  | CTC General Reserve | Additional two changing Rooms |  | 301750
2024-05-25 | Studio Four | 15901-42019 | Pre-Construction Stage 40% of £3,200 Contract Preparation 100% of £600 | 1880
2022-05-27 | Healthmatic | 11853 | Design & Build Contract Delivery Contract Milestone Payment 2 | 17338.2941 |  |  |  | Ingrams Pavilion Contributions
2022-07-15 | Healthmatic | 12053 | Design & Build Contract Delivery Contract Milestone Payment 3 | 17907.17 |  |  |  | East Devon District Council
2022-07-14 | Studio Four | 16036-42019 | Pre-Construction Stage 20% of £3,200 | 640 |  |  |  | Provision of NEAPs |  |  | 581
2024-08-22 | Studio Four | 16036-42019 | Pre-Construction Stage 20% of £3,200 | 640 |  |  |  | Public art contribution |  |  | 75000
2022-08-24 | Healthmatic | 12174 | Design & Build Contract Delivery Contract Milestone Payment 4 | 50802.28 |  |  |  | Youth play areas |  |  | 95554
2024-08-31 | Peter Woodman | Pro Forma Inv 72 | 50% Deposit Payment Sep/Oct 22 |  | 1440 |  |  | Received August 2021 |  |  | 171135
2022-09-14 | Studio Four | 16229-42019 | Additional Meetings |  | 720 |  |  | EDNCP Contributions
2022-09-22 | Tony Benger Landscaping | 32264 | Re-adjustment of the Ingrams Gate |  | 81.73 |  |  | Pavilion |  |  | 600000
2022-10-17 | Healthmatic | 12337 | Design & Build Contract Delivery Contract Milestone Payment 6 | 262486.55 |  |  |  | Leisure Facilities |  |  | 150000
2022-09-14 | Healthmatic | 12232 | Design & Build Contract Delivery Contract Milestone Payment 5 | 50385.94 |  |  |  | Received 2021-22 |  |  | 750000
2022-11-04 | Healthmatic | 12404 | Design & Build Contract Delivery Contract Milestone Payment 7 | 226825.82 |  |  |  | Contribution from Council’s general reserves (minute 22/101) |  |  | 301750
2024-10-27 | Stephens Scown | 184392 | Sports Pavilion Licence |  | 500 |  |  | Sport England grant |  |  | 125000
2022-11-14 | Studio Four | 16408-42019 | Construction Stage 20% of £4,960 | 992 |  |  |  | Total: |  |  | 1347885
|  |  | Drainage Design |  | 1720
2022-12-09 | Healthmatic | 12508 | Design & Build Contract Delivery Contract Milestone Payment 7 | 256890.25
2023-01-18 | Healthmatic | 12585 | Design & Build Contract Delivery Contract Milestone Payment 9 | 142547.2
2023-01-06 | Peter Woodman | Invoice 90 | Visit 20 Oct 22 and 5 Jan 23 |  | 197.5
2023-01-18 | Studio Four | 16582-42019 | Construction Stage 60% of £4,960 | 2976
2023-02-07 | Healthmatic | 12644 | Design & Build Contract Delivery Contract Milestone Payment 10 | 78078.99
2023-01-14 | M.A.T. Electrics Ltd | Q16030/2/TJ | Devon Air Ambulance Landing Site Lighting |  | 6002.11
2024-07-12 | Healthmatic | 13027 | Design & Build Contract Delivery Contract Milestone Payment 10 | 137734.09
2023-06-20 | Studio Four | 17026-42019 | Construaction Stage Queries/ Storage Area/ Site Services |  | 705
2023-05-13 | Power Precision and Fabrication Ltd | 230534 | Roller (23/34a) |  | 3895
2023-07-07 | Ayre Contractors & Plant | 2680 | Storage Compound Base (23/59) |  | 5400
2023-08-23 | Cleveland Containers | 139443 | 20ft Tri-Door Container(23/50) |  | 8795
2023-07-27 | Tamar Security | 115170 | CCTV installation 1st fix in Jan 2023 |  | 450
2024-09-01 | Quick Plant & Groundworks Ltd | INV-0549 | Hire of Security Fence Panels 01/07/23-02/09/23 |  | 472.5
2023-09-20 | Studio Four | 17315-42019 | Storage Area |  | 237.5
2023-10-02 | Quick Plant & Groundworks Ltd | INV-0569 | Hire of Security Fence Panels 03/09/23-02/10/23 |  | 210
2023-11-20 | Quick Plant & Groundworks Ltd | INV-0592 | Hire of Security Fence Panels 03/10/23-02/11/23 |  | 367.5
2024-01-03 | Quick Plant & Groundworks Ltd | INV-0607 | Hire of Security Fence Panels 21/11/23-02/01/24 |  | 315
2023-12-19 | Studio Four | 17563-42019 | Construaction Stage Queries |  | 280
2024-01-12 | Football Foundation |  | Grants for Storage Containters |  |  | 6596
2024-01-11 | Amazon |  | Padlocks |  | 17.46
2024-01-23 | IKEA |  | Mugs/Glasses/Servewear Sets |  | 298.33
2024-01-23 | Screwfix | A16043836757 | Push-Button Locks |  | 287.1
2024-01-23 | Amazon |  | Knives Set |  | 12.37
2024-01-23 | Amazon |  | Kitchen Utensils |  | 12.49
2024-01-23 | Amazon |  | Pots and Pans Set |  | 45.97
2024-01-23 | Currys | 525993 | Cooker/ Fridge / Cooker Hood |  | 551.67
2024-01-23 | Nisbets | UK15793064 | Microwave/ Kettle/ Basin Taps/ Drainer |  | 487.96
2024-01-23 | Amazon |  | Plastic Tumblers |  | 33.16
2024-01-23 | Nisbets | 26886863 | Cutlery |  | 53.99
2024-01-31 | Quick Plant & Groundworks Ltd | INV-0618 | Hire of Security Fence Panels 03/01/24-31/01/24 |  | 210
2024-02-05 | Adexa Direct | 1112070 | Commercial Worktop Cupboard |  | 480
2024-02-26 | Toolstation | XWW579274215 | Heras Fencing Tool |  | 14.15
2024-03-31 |  |  | From General Reserve (24/42) |  |  | 50000
2023-03-27 | Studio Four | 16768-42019 | Construction Stage 20% of £4,960 | 992
2024-03-18 | Gopak Ltd | 647621 | Folding Tables (6 x Rounds, 6 x Retangles ) |  | 2433.4
2024-03-21 | Quick Plant & Groundworks Ltd | INV-0644 | Hire of Security Fence Panels 01/02/24-20/03/24 |  | 367.5
2024-03-28 | Furniture@Work Ltd | INV0608005 | Conference Chairs |  | 2685
2024-05-10 | Stalite Signs | 116957 | Ingrams Sports Pitches Sign |  | 956.89
2024-05-09 | The Metal Store | 751825 | Ingrams Signs Post Poles |  | 96.5
2024-05-08 | B&Q |  | Ingrams Postcrete |  | 34.85
2024-05-17 | Quick Plant & Groundworks Ltd | INV-0662 | Hire of Security Fence Panels 21/03/24-16/05/24 |  | 420
2024-04-19 | Garden Express | 185662 | Ingrams Plants |  | 1101.11
2024-04-29 | Screwfix | A17656806262 | Ingrams Rechargable Lights |  | 69.98
2024-04-19 | B&Q | 1039711253 | ingrams Compost & Mulch |  | 135
2024-04-26 | Sign Trade Supplies Ltd | INV-332253 | Ingrams Signs Rails & Fixing |  | 41.91
2024-05-28 | Tony Benger Landscaping | 40503 | Ingrams Additional Works |  | 1194
2024-05-28 | Tony Benger Landscaping | 40502 | Ingrams Landscaping b/w Pavilion and Pitches |  | 1694.32
2024-06-21 | Wicks |  | Ingrams Hose and Connector |  | 92.26
2024-06-28 | G.J. Waller & Co | 2073 | Install Garden Tap at Ingrams |  | 42
2024-06-28 | Studio Four Architects Ltd | 18067-42019 | Construction Stage Queries |  | 280
2024-07-29 | Studio Four Architects Ltd | 18142-42019 | Heating System Redesign |  | 1000
2024-08-12 | Healthmatic | 13972 | Design & Build contract delivery Interim Payment Notice - Certificate No.12 | 36779.73
2024-08-19 | Amazon Business EU S.à.r.l |  | Pump Action Pressure Sprayer |  | 11.62
2024-08-19 | Agri-Gem Ltd |  | Roundup Pro Active |  | 57.99
2024-08-19 | Quick Plant & Groundworks Ltd | INV-0694 | Hire of Security Fence Panels 17/05/24-16/08/24 |  | 682.5
2024-08-21 | Studio Four Architects Ltd | 18201-42019 | Heating system redesign |  | 300
2024-09-11 | Studio Four Architects Ltd | 18265-42019 | Heating system redesign |  | 100
2024-09-17 | Healthmatic | 14063 | 35% On Acceptance of quote |  | 11941.8635
|  |  |  | 1333087.2941 | 60032.1835 | 1407330.47
|  |  |  | Total Expenditure | 1393119.4776
|  |  |  | Balance |  | 14210.9924 | EMR 337- Ingrams Pavilion
Expected Balance Payment
|  |  |  | Tamar Security | 5236.17
|  |  |  | Studio Four | 760
|  |  |  | Healthmetic | 22177.75
|  |  |  | Total | 28173.92
|  |  |  | Expected Balance |  | -13962.9276

## Tamar Security
Tamar Security
Contract Amount |  |  | 5686.17
Invoice Date | Invoice No. | Descaption | Net Amount | VAT | Total
2023-07-27 | 115170 | CCTV Installation 1st Fix in Jan 2023 | 450 | 90 | 540
|  | Total Paid | 450
|  | Balance for payment | 5236.17

## Studio Four
Studio Four |  | 21/02/2022 (22/44)
Proposal Date |  | 2022-02-07 | [5 empty] | Pre-Consturciton State | 3200
Scope of project |  | Construction of new sports pavilion, car park and associated landscaping | [5 empty] | Contract Preparation | 600
Budget |  | 895000 | [5 empty] | Construction State | 4960
[8 empty] | Completion and defects | 1040
Invoice Date | Invoice No. | Description | Net Amount | Addition | VAT | Total Amount | SOP |  | 9800
2022-04-28 | 15832-42019 | Pre-Construction Stage 20% of £3,200 | 640 |  | 128 | 768 | 2022-05-23
|  | Addition Documents : 2 x JCT Design Contract 2016 |  | 152 | 30.4 | 182.4
2022-05-25 | 15901-42019 | Pre-Construction Stage 40% of £3,200 | 1280 |  | 256 | 1536 | 2022-06-27
|  | Contract Preparation 100% of £600 | 600 |  | 120 | 720
2022-07-14 | 16036-42019 | Pre-Construction Stage 20% of £3,200 | 640 |  | 128 | 768 | 2022-07-25
2022-08-22 | 16156-42019 | Pre-Construction Stage 20% of £3,200 | 640 |  | 128 | 768 | 2022-08-22
2022-09-14 | 16229-42019 | Addition Meetings |  | 720 | 144 | 864 | 2022-09-26
2022-11-14 | 16408-42019 | Construction Stage 20% of £4,960 | 992 |  | 198.4 | 1190.4 | 2022-11-21
|  | Drainage Design |  | 1720 | 344 | 2064
2023-01-18 | 16582-42019 | Construcation Stage 60% of £4,960 | 2976 |  | 595.2 | 3571.2 | 2023-01-23
2023-03-27 | 16768-42019 | Construction Stage 20% of £4,960 | 992 |  | 198.4 | 1190.4 | 2023-04-24
2023-06-20 | 17026-42019 | Construction Stage Queries |  | 40 | 8 | 48 | 2023-06-26
|  | Storage Area |  | 95 | 19 | 114
|  | Site Services |  | 570 | 114 | 684
2023-09-20 | 17315-42019 | Storage Area |  | 237.5 | 47.5 | 285 | 2023-09-25
2023-12-19 | 17563-42019 | Construction Stage Queries |  | 280 | 56 | 336 | 2024-01-22
2024-06-28 | 18067-42019 | Construction Stage Queries Agreed Capped Time Charge £600 Previously Invoiced £320 GJ 10 Hours @£80 | 280 |  | 56 | 336 | 2024-07-22
2024-07-29 | 18142-42019 | Heating system redesign |  | 1000 | 200 | 1200 | 2024-08-19
2024-08-21 | 18201-42019 | Heating system redesign |  | 300 | 60 | 360 | 2024-09-23
2024-09-11 | 18265-42019 | Heating system redesign |  | 100 | 20 | 120 | 2024-09-23
|  | Total | 9040 | 5214.5 | 14254.5
|  | Balance payment | 760

## Healthmatic
Healthmatic Ltd | [8 empty] | From email dated 3 November 2022
Invoice Date | Invoice Number | Description | Net Amount | Retention 3% | Sub Total | VAT | Total |  | Forcast Payment Schedule
2022-04-19 | 11728 | Design & Build Contract Delivery Contract Milestone Payment 1 | 47834 | 1435.02 | 46398.98 | 9279.796 | 55678.776 |  | Date |  | Value | Invoice Net Amount
2022-05-27 | 11853 | Design & Build Contract Delivery Contract Milestone Payment 2 | 17874.53 | 536.2359 | 17338.2941 | 3467.6588 | 20805.9529 |  | 2022-04-23 | Payment 1 | 47834 | 46398.98
2022-07-15 | 12053 | Design & Build Contract Delivery Contract Milestone Payment 3 | 17907.17 |  | 17907.17 | 3581.434 | 21488.604 |  | 2022-05-21 | Payment 2 | 17338 | 17338.29
2022-08-24 | 12174 | Design & Build Contract Delivery Contract Milestone Payment 4 | 50802.28 |  | 50802.28 | 10160.456 | 60962.736 |  | 2022-06-25 | Payment 3 | 18461 | 17907.17
2022-10-17 | 12337 | Design & Build Contract Delivery Contract Milestone Payment 6 | 262486.55 |  | 262486.55 | 52497.31 | 314983.86 |  | 2022-07-23 | Payment 4 | 51154 | 50802.28
2022-09-14 | 12232 | Design & Build Contract Delivery Contract Milestone Payment 5 | 50385.94 |  | 50385.94 | 10077.188 | 60463.128 |  | 2022-08-20 | Payment 5 | 51944 | 50385.94
2022-11-04 | 12404 | Design & Build Contract Delivery Contract Milestone Payment 7 | 226825.82 |  | 226825.82 | 45365.164 | 272190.984 |  | 2022-09-26 | Payment 6 | 240239 | 262486.55
2022-12-09 | 12508 | Design & Build Contract Delivery Contract Milestone Payment 8 | 256890.25 |  | 256890.25 | 51378.05 | 308268.3 |  | 2022-10-26 | Payment 7 | 264795 | 226825.82
2023-01-18 | 12585 | Design & Build Contract Delivery Contract Milestone Payment 9 | 142547.2 |  | 142547.2 | 28509.44 | 171056.64 |  | 2022-11-26 | Payment 8 | 264795 | 256890.25
2023-02-07 | 12644 | Design & Build Contract Delivery Contract Milestone Payment 10 | 78078.99 |  | 78078.99 | 15615.798 | 93694.788 |  | 2022-12-23 | Payment 9 | 198597 | 142547.2
2023-07-12 | 13027 | Design & Build Contract Delivery Contract Milestone Payment 10 | 137734.09 |  | 137734.09 | 27546.818 | 165280.908 |  | 2023-01-26 | Payment 10 | 119158 | 78078.99
2024-08-12 | 13972 | Design & Build contract delivery Interim Payment Notice - Cert. No 12 | 36779.73 |  | 36779.73 | 7355.946 | 44135.676 |  | 2023-02-26 | Payment 11 | 49662 | 137734.09
[10 empty] | Total | 1323977 | 1287395.56
|  | Total | 1326146.55 | 1971.2559 | 1324175.2941 | [5 empty] | Balance to pay: | 36581.44
|  |  |  | New Contract total | 1320410.72
|  |  |  | Balance | -3764.5741
Ingrams Pavilion Additional Heating Installation PO:ING-2024-25 |  |  | 34119.61
Invoice Date | Invoice Number | Description | Net Amount |  |  | VAT | TOTAL | SOP
2024-09-17 | 14063 | 35% On Acceptance of quote | 11941.8635 |  |  | 2388.3727 | 14330.2362 | 2024-09-23
|  | 30% 1 month prior to installation of ASHP | 10235.883 |  |  | 2047.1766 | 12283.0596
|  | 32% When installation is complete and O&M’s handed over | 10918.2752 |  |  | 2183.655 | 13101.9302
|  | 3% 6 months after installation and handover of O&M’s | 1023.5883 |  |  | 204.7177 | 1228.306
|  | Balance to pay | 22177.7465

## Playinnovation
Ingrams MUGA
PlayInnovation Ltd
Minutes Ref: (24/128 )
S106 Agreement
Total Cost | 169049.08
|  |  |  | Inv Date | Inv No | SOP
Payment 1 | at point of order | 25% | 42262.27 | 2024-10-01 | 190275 | 2024-10-21
Payment 2 | to be paid withing 5 working days of commencement of works | 25% | 42262.27
Payment 3 | to be paid within 14 business days of sign off for practical completion and safety inspection by RoSPA. | 45% | 76072.086
Payment 4 | to be paid once access control system by Bookteq has been installed. | 5% | 8452.454
169049.08

## Peter Woodman
Peter Woodman
Invoice Date | Invoice No. | Description |  |  |  |  | Amount | SOP
2022-08-31 | Pro Forma Inv 72 | 50% Deposit Payment |  |  |  |  | 1440 | 2022-09-26
2022-08-31 | Invoice 80 | Revised costs for items 1 to 8 of general quotation of 30 August 2022 = £1,630.00 Balance Due |  |  |  |  | 190 | 2022-10-24
2022-10-20 | Invoice 83 | Cricket Pitch Maintenance as per email of 20 October 2022 |  |  |  |  | 250 | 2022-10-24
2023-01-06 | Invoice 90 | Visit 10 Nov 22 and 5 Jan 23 |  |  |  |  | 197.5 | 2023-01-23
2023-04-24 | Invoice 95 | Cricket Pitch Maintenance |  |  |  |  | 400 | 2023-04-24
2023-07-21 | Invoice 107 | Cricket Pitch Maintenance May to July 2023 |  |  |  |  | 1230 | 2023-07-24
Cranbook | Ground Budget (SQUARE) Sept 2023 to August 2024 (Estimated)
END OF SEASON, OVERWINTER AND PLAY IN FULL FROM MID APRIL IN 2024 SEASON (40 matches)
Date : 9 August 2023
(23/151)
Expenditure | Aug | Sep | Oct | Nov | Dec | Jan | Feb | March | April | May | June |  | July | Aug |  | Total
Labour and machinery supply |  | 250 | 250 | 250 | 200 | 200 | 200 | 975 | 975 | 975 | 975 |  | 975 | 975 |  | 7200
Machinery supplied |  | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 |  | 120 | 120 |  | 1200
Travel costs |  | 80 | 80 | 80 | 80 | 80 | 80 | 140 | 140 | 140 | 140 |  | 140 | 140 |  | 1320
Loam | Sep: 50; March: 15; April: 10; June: 10 |  | 15 |  |  | 100
Fertiliser | Sep: 60; Nov: 60; March: 60; May: 60 |  | 60 |  |  | 300
Seed | Sep: 100; April: 50; May: 50 |  | 100 |  |  | 300
Paints and line marker | April: 30; May: 35; June: 35 |  | 35 | 35 |  | 170
Fuel |  | 20 | 20 | 20 | 20 | 20 | 20 | 40 | 40 | 40 | 40 |  | 40 | 40 |  | 360
Misc |  | 20 | 20 | 20 | 20 | 20 | 20 | 30 | 30 | 30 | 30 |  | 30 | 30 |  | 300
Aeration | Nov: 120; Dec: 120 |  |  |  |  | 240
End of Season (Labour/machinery) | Sep: 300 |  |  |  |  | 300
Total budget |  | 960 | 450 | 630 | 520 | 400 | 400 | 1380 | 1395 | 1450 | 1350 |  | 1515 | 1340 |  | 11790
Invoice Date | 2023-10-10 |  |  | 2023-11-30 | 2024-01-05 | 2024-02-29 |  | 2024-04-02 | 2024-04-30 | 2024-05-30 | 2024-06-11 | 2024-07-11 | 2024-08-11 | 2024-09-03 | 2024-09-30
Invoice Number | 123 |  |  | 129 | 135 | 144 |  | 148 | 152 | 156 | 160 | 163 | 167 | 169 | 172
Amount | 787 |  |  | 536 | 220 | 120 |  | 420 | 2510 | 3565 | 1023 | 2872.5 | 2867.5 | 1794 | 3850 | 20565 | Total
Schedule of payments | 2023-10-30 |  |  | 2023-12-11 | 2024-01-22 | 2024-03-18 |  | 2024-04-22 | 2024-05-13 | 2024-06-24 | 2024-06-24 | 2024-07-11 | 2024-08-19 | 2024-09-23 | 2024-10-21
[8 empty] | Square | 1395 | 1400 | 495 | 1432.5 | 1427.5 | 865 | 1910
[8 empty] | Outfield | 1115 | 2165 | 528 | 1440 | 1440 | 929 | 1940
[9 empty] | Invocie 153 | Invoice 155 | *1 to 11 June | 12 Jun to11 Jul | 12 Jul to 11 Aug | 12 Aug to 31 Aug | Sept 2024
[9 empty] | Cricket Equpiment | Extras for May
[9 empty] | 540.17 | 861.33
[9 empty] | SOP 13 May 2024 | SOP 24 June 2024
Notes
1 |  | Excludes any "outfield" costs or activity - so EXCLUDES hire of outfield roller or cutting
2 |  | In play labour charge will vary plus/minus according to games played.

## Persimmon -Community Champions
Persimmon Homes Ltd
Community Champions
Date | From | Description
2024-05-15 | Persimmon | Cheque from Persimmon |  | 1500
2024-04-30 | Peter Woodman | Cricket Equipment | 540.17
|  |  | 540.17 | 1500
|  |  | Balance: | 959.83