## Sheet1
ASSETS DELIVERY WORKING GROUP
CRANBROOK TOWN COUNCIL
28 April 2025
ADOPTION
Asset | Snagging | Delivery Date | Current Position | Comments
Land transfers of public open space |  |  | Awaiting the transfer document (TP1) for remaining car parking spaces at St Martin's and open spaces at Little Mead, the junction of Yonder Acre Way and Rush Meadow Road and the rectification of the rectification of the Tillhouse Farm boundary from the consortium's solicitor
Tulip Way development | Gabion wall finishing and future adoption by Devon County Council. Issues around access to potential areas of public open space across private land. Transfer of areas of public open space to social housing provider. Safety barrier along north boundary of Ecology Park. Identification of areas of public open space to be adopted by Cranbrook Town Council. |  | Agreement between Taylor Wimpey, Devon County Council and planning authority (East Devon District Council) to decommission ramp on parcel 7 because it connects to private land, and create new access point to green lane.
Persimmon Parcel - phase 4 - Cedar Close parking on planned Public Open Space |  |  | Design proposals agreed to create permeable parking areas on the existing grass verge. General approach agreed - acceptable to Town Council to manage the remaining verge and hedgerow as and when transferred by Persimmon. Persimmon report having instructed contractor.
COUNTRY PARK & NATURE RESERVE
Asset | Snagging | Delivery Date | Current Position | Comments
Sustainable Urban Drainage Systems (Phases 2 & 3 as per plan 30) | Phase 2 (Stone Meadow) & the small basin off Westland Way/Crannaford Lane, town centre basins | Basins 2A/B/C. Planning Permission granted for extension of basin 2C. Awaiting timescales for work. Town centre basins awaits construction.
Sustainable Urban Drainage Systems (Phases 2 & 3 as per plan 30) | Phase 3 (Ecology Park, Platinum Park, Island Avenue, Ingrams, Yonder Acre Way, new basin in parcel TC7) | Awaits completion of the Ecology Park basins and drainage system (including the syphon and Viewing Platform), plus the yet to be constructed basins north of Ingrams and in parcel TC7
SPORTS
Asset | Snagging | Delivery Date | Current Position | Comments
Ingrams LEAP (Local Equipped Area for Play) |  |  | Tender live on Find a Tender until 14 April 2025
Ingrams Pavilion |  |  | Mains electricity connected; awaiting meter installation and final commissioning works (electricity, plumbing and water connection to cricket square)
PLAY PARKS
Asset | Snagging | Delivery Date | Current Position | Comments
Neighbourhood Equipped Area of Play (NEAP) within Stone Meadow Country Park |  |  | Expansion plans for basin 2C should accommodate Neighbourhood Equipped Area of Play/Conversation with planning authority regarding possible re-location of 2nd NEAP elsewhere
Local Equipped Area of Play for Town Centre/Cranbrook Education Campus |  |  | Trigger 3,250 homes - awaiting planning approval for attenuation tank to be installed before works to deliver play park can commence
INFRASTRUCTURE
Asset | Snagging | Delivery Date | Current Position | Comments
Town square |  |  | Land transfer progressing; Town Council awaiting transfer of Town Square Commuted Sum and Bond, lift warranty and lift service agreement
Delivery of The Tillhouse |  |  | Concept design on parcel TC2 produced; meeting scheduled with the East Devon New Community Partners
Cranbox |  |  | East Devon District Council leading on the delivery of commercial modular units
Provision for Scout hut |  |  | Planning authority confirmed that the hut is not included in the infrastructure delivery plan attached to the Cranbrook Plan and that they are not including the provision in any Section 106 negotiations relating to the expansion areas
Delivery of grounds maintenance compound
Southbrook Allotments |  |  | Await handover of allotments subject to non-material amendment (NMA) to planning consent
CCTV |  |  | Assessing CCTV provision for skatepark and play areas. Installation at the town square progressing. Discussions continue with the consortium who are obligated to provide electricity and water connections to play parks